## Cover Page
Online Grocery Store
Sprint Backlog
|  | Prepared By / Last Updated By | Reviewed By | Approved By
| Name | Riya,Kavya,Vaibhav,Sumanth,Teja
| Role | Software Developer
| Signature | Riya,Kavya,Vaibhav,Sumanth,Teja
Date
:
Controlled copy
Controlled copy
Controlled copy
Controlled Copy

## Instructions
Sprint Backlog - Instructions C3: Protected Controlled Copy
Sprint Backlog
The Sprint Backlog is the set of Product Backlog items selected for the Sprint, plus a plan for delivering the product Increment and realizing the Sprint Goal. The Sprint Backlog is a forecast by the Development Team about what functionality will be in the next Increment and the work needed to deliver that functionality into a “Done” Increment.The Sprint Backlog is the output of the sprint planning meeting. It is essentially the list of tasks that the Scrum team needs to complete during the sprint in order to turn a selected set of product backlog items into a deliverable increment of functionality.
Sample
The sheet sample is an example sheet on how to fill the sprint backlog. Trainees can refer it to fill the details in the sheets Sprint 1/2/3.
Sprint 1/2/3
| User Story & Task Id | List the User Story id taken from product backlog that are selected to be completed in the particular sprint & List the number of tasks the User story is split into..
| Task | Name the tasks the user story is split into.
| Story Points | Enter the story points that was given for the user story during Sprint planning
| Assigned to | Name the person responsible for the particular task
| Status | Status of the Task - In progress/Completed
| Original Estimate | Original estimate of the task
| Day 1/2/3/4/5 | Task done in Day1/2/3/4/5 - Sprint review and retrospective to be held on Day 5
| Total | Summation of the estimation per day. To be filled with the total of the estimations filled.
| Charts | Chart is self driven as per the task burned

## Sample
Sprint Backlog Online Grocery Store Project ID: AJ016 C3: Protected Controlled Copy
USER STORY & TASK ID | USER STORY & TASK | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5
US_1 | User Registration | 8
Task_1 | Create table to store registration details |  | Trainee_1 |  | 7 | 5 | 3 | 0 | 0 | 0
Task_2 | Design the registration page |  | Trainee_2 |  | 3 | 1 | 1 | 5 | 0 | 1
Task_3 | Design Login page |  | Trainee_1 |  | 1 | 0.5 | 0 | 3 | 0 | 0
Task_4 | Develop authentication process for login |  | Trainee_2 |  | 0.5 | 1 | 2 | 3 | 1 | 0
US_2 | Admin Home | 1
Task_1 | Create table to store Admin details |  | Trainee_3 |  | 3 | 3 | 0.5 | 0.5 | 0 | 0
Task_2 | Design the Admin registration page |  | Trainee_4 |  | 3 | 5 | 5 | 1 | 1 | 1
Task_3 | Develop code for authentication |  | Trainee_3 |  | 2 | 2 | 5 | 0 | 1 | 0
Task_4 | Develop code to store the admin details |  | Trainee_4 |  | 5 | 5 | 9 | 5 | 1 | 0
US_3 | Listing courses | 5
Task_1 | Develop code for Admin or vendor to add a course |  | Trainee_1 |  | 8 | 6 | 0 | 0 | 0 | 0
Task_2 | Develop Code ofr Admin or vendor to edit a course |  | Trainee_2 |  | 3 | 1 | 3 | 3 | 3 | 0
Task_3 | Develop code for - On clicking on edit a form should be pop up With valid input clicking on Add/update will update the database |  | Trainee_3 |  | 1.5 | 1 | 0.5 | 0.5 | 1 | 1
Task_4 | Develop code for Admin or vendor to activate or deactivate a course |  | Trainee_4 |  | 2 | 0.5 | 0 | 0 | 0 | 0
US_4 |  | 8
Task_1 |  |  |  |  | 9 | 4 | 2 | 2 | 1 | 1
Task_2 |  |  |  |  | 6 | 6 | 3 | 3 | 3 | 1
Task_3 |  |  |  |  | 6 | 2 | 8 | 8 | 1 | 0
Task_4 |  |  |  |  | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0
US_5 |  | 3
Task_1 |  |  |  |  | 2 | 1 | 1 | 1 | 0.5 | 1
Task_2 |  |  |  |  | 6 | 6 | 6 | 0.5 | 3 | 9
Task_3 |  |  |  |  | 9 | 9 | 9 | 4 | 3 | 3
Task_4 |  |  |  |  | 0.5 | 0.5 | 0.5 | 1 | 0.5 | 0
TOTAL |  |  |  |  | 78 | 60 | 59 | 41 | 20 | 18

## Sprint -1
Sprint Backlog Online Grocery Store Project ID: AJ016 C3: Protected Controlled Copy
BACKLOG TASK & ID | USER STORY & TASK | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5
User Story #1 | Admin Login | 3
Task_1 | Design the registration page |  | Riya Dighe |  | 15 | 5 | 3 | 2 | 2 | 3
Task_2 | Design login page |  | M.S. Sai Kavya |  | 14 | 2 | 2 | 4 | 4 | 2
Task_3 | Validation |  | Vaibhav Shetty |  | 12 | 4 | 2 | 1 | 2 | 3
User Story #2 | User Signup | 5
Task_1 | Create table to store User data |  | M.S. Sai Kavya |  | 13 | 2 | 4 | 4 | 2 | 1
Task_2 | Design the registration page |  | Vaibhav Shetty |  | 18 | 3 | 5 | 4 | 2 | 4
Task_3 | Validation |  | Riya Dighe |  | 11 | 3 | 2 | 3 | 2 | 1
User Story #3 | User Login | 8
Task_1 | Design login page |  | Teja Mani |  | 12 | 2 | 2 | 3 | 3 | 2
Task_2 | Validation |  | Sumanth |  | 13 | 2 | 2 | 2 | 3 | 4
User Story #4 | Changing User Details | 5
Task_1 | Updating password |  | Vaibhav |  | 11 | 2 | 3 | 2 | 3 | 1
Task_2 | Validation |  | Sumanth |  | 12 | 1 | 3 | 2 | 3 | 3
User Story #5 | Placing the order | 5
Task_1 | Creating product table to view products |  | Riya Dighe |  | 20 | 3 | 4 | 3 | 5 | 5
Task_2 | Design cart page |  | M.S. Sai Kavya |  | 15 | 2 | 2 | 3 | 4 | 4
Task_3 | Validation |  | Vaibhav |  | 11 | 1 | 2 | 3 | 3 | 2
User Story #6 | Viewing Order status | 8
Task_1 | Creating orders table |  | Vaibhav Shetty |  | 10 | 4 | 2 | 1 | 1 | 2
Task_2 | Design order status page |  | Teja Mani |  | 13 | 4 | 2 | 3 | 1 | 3
TOTAL |  |  |  |  | 177 | 32 | 36 | 36 | 38 | 35

## Sprint -2
Sprint Backlog <Project name> Project ID: <Batch code/project id> C3: Protected Controlled Copy
BACKLOG TASK & ID | USER STORY & TASK | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5
User Story #1
Task_1
Task_2
Task_3
Task_4
User Story #2
Task_1
Task_2
Task_3
Task_4
User Story #3
Task_1
Task_2
Task_3
Task_4
User Story #4
Task_1
Task_2
Task_3
Task_4
User Story #5
Task_1
Task_2
Task_3
Task_4
TOTAL |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0

## Data (hidden)
In-Progress
Completed
N/A