## Cover Page
<Project Name>
Product Backlog
|  | Prepared By / Last Updated By | Reviewed By | Approved By
| Name | Dighe Riya Marrivada Sai Kavya Sumanth Mittapally Teja Jami Vaibhav Shetty
| Role | Software Developer
| Signature | Dighe Riya - 2065747 Marrivada Sai Kavya - 2065919 Sumanth Mittapally - 2065743 Teja Jami - 2066007 Vaibhav Shetty - 2065774
| Date | 2022-01-12
Release ID: QTAD-PBL / 2.0.0 / 30-Mar-2015 |  |  |  | C3: Protected
Controlled copy
Controlled copy
Controlled copy
Controlled Copy

## Instructions
Product Backlog Instructions C3: Protected Controlled Copy
Backlog Worksheet
This sheet has to be filled while doing "Create Product Backlog" task in the Initial Envisioning Phase.
The Product backlog worksheet contains a list of features/requirements that the business would want to implement in an application. This worksheet would continue to exist from the beginning to the end of the project. The Product Owner maintains it by adding, modifying, removing any of the items listed there. They can also change the priority of the items so long as they are not being worked by the team in the ongoing Sprint. Most of the re-ordering would happen just before the Sprint Planning meeting. To ensure this kind of continuous update, this worksheet could be re-visited during periodic intervals once during the release elaboration Phase and thereafter during the project execution. The changes to the Product backlog could be triggered from several sources in terms of inclusion of new features / bugs/ known issues based on the stakeholder requests and the effort, schedule for the same would also be re-visited in the product backlog worksheet. Fill the following fields in the product backlog worksheet for each feature.
| User Story ID | <Provide unique ID for each User story>
| User Story Name | <Provide the theme/name of the User story or a high level requirement> Eg: User login Registration Mail notification
| User Story Role | < Provide who would be end User of the User story>. Details of who would use that functionality Eg:End User Admin Teacher Conference attendee
| User Story Details | <Provide description of what the User want> Provide details on "As a/an" particular user what the user wants. Eg: As a conference attendee, I want to be able to register online
| Acceptance criteria | <Specify the Acceptance criteria> Acceptance criteria define the boundaries of a user story, and are used to confirm when a story is completed and working as intended. So for the above example, the acceptance criteria could include: A user cannot submit a form without completing all the mandatory fields Information from the form is stored in the registrations database.
| Sprint | Sprint in which the user story is planned to completed. Select it from the drop down. Story Point is given in Fibonacci series of upto 21. For any User story if the estimation goes beyond 21, then the user story has to be broken down.
| Story point | A story point is a metric used in agile project management and development to determine (or estimate) the difficulty of implementing a given story. Select the story point that will be assigned to the user story from the drop down (in Fibonacci series) during the sprint planning meeting while estimating an user story.
| Done | Yes/No field, that can be selected from drop down based on an user is completed or not
| Added in Sprint | Provide sprint number when the particular User Story was handled
| Closed in sprint | Provide sprint number when the particular User Story was completed
| Actual Story Points | Actual story point burned for an user story while developing. Select from the drop down (in Fibonacci series)
Charts
| Sprint | This value is non-editable. Represents the Sprint numbers
| Story Points remaining | Enter the total story points calculated for the Sprint.
| Done | Enter the total story points that was "Done" in the sprint
| Variation | This value is non-editable. Variation is calculated as [(Current sprint's story point remaining + done) - (Previous sprint's story point remaining + done) + Previous sprint's variation]
| Percent Complete | Percentage completed is calculated as [(Done story point of the sprint/(Done story point + story point remaining)) *100]
| Release Burn Down Chart | 1. A typical release Burn Down chart would enable the Product Owner to assess as to how each iteration is progressing towards realizing the release goal. They would be able to assess the number of features that are going to make it (or) not make it to the release based on the number of features delivered by the team in each iteration. 2. Based on the progress being made by the team, the Product Owner may decide to add more Sprints within a release (if it is a feature driven release) or cut down some of the features from the Release backlog (if it is a Date driven release). The release burn down chart would be automatically plotted based on the data given on the Release burn down table with story points remaining and the done.

## Backlog
Product Backlog Online Grocery Store Project ID: ADM21AJ016 C3: Protected Controlled Copy
Done
User Story Id | User Story Name | User Story Role | User Story Details | Acceptance criteria | Priority | Sprint | Story Point | Done | Added in Sprint | Closed in sprint | Actual Story Points
US_1 | Admin Login | Admin | Ability of the system to, admin need to login to access the application | 1. Email Id and password are needed. 2. If the email id and password are correct ,it will be redirected to the home page of the application. 3. If the email id and password are incorrect, it will not be redirected to the home page and it shows an incorrect username or password in same login page. | Critical | Sprint 1 | 3
US_2 | User Signup | User | Ability of the system to, user should signup to use the application by their email id in order to use the application. | 1. Name, Email, Mobile number, Security question, Answer and Password are required. 2. Password should be of minimum 8 characters(must includes capital, symbols,numbers) 3. If the given details are correct then it shows "registered successfully" in the same page 4. Database will store all the details. | High | Sprint 1 | 5
US_3 | User login | User | Ability of the system to, user should Login to use the application and place the order. | 1. Email Id and password are needed. 2. If the email id and password are correct ,it will be redirected to the home page of the application. 3. If the email id and password are incorrect, it will not be redirected to the home page and it shows an incorrect username or password in same login page. | Medium | Sprint 1 | 8
US_4 | Changing user details | User | Ability of the system to, as the user who signed up the application can able to change the password | 1. The user can change the details. 2. In home page, there will be a option named "Change Password". 3. The user can able to change the details and save it. Here only the user has the access to view this page. | High | Sprint 1 | 5
US_5 | Placing the order | User | Ability of the system to, as a user they will be able to place the order as per their requirement. | 1. Based on their needs and available menu the user can place the order. 2. During the order of groceries they shall search for their need and add their favourites in the cart also. 3. And they able to see their orders in option called My cart | High | Sprint 1 | 5
US_6 | Viewing order status | User | Ability of the system to,the user will be able to view the products they ordered. | 1. The user will be able to view the product name,category and Price 2. The user can also able to view order date,expected delivery date,Payment method and statusof the order . 3. The user can view these details under the option called My orders. | Medium | Sprint 1 | 8
US_7 | Order cancellation | User | Ability of the system to,as a user they should be able to cancel the order. | 1. After placing the order, there will a option called Remove for the users to cancel the order. 2. If the user click Remove, Product remove from My Cart | Low | Sprint 2 | 13
US_8 | Order cancellation | Admin | Ability of the system to, as a admin should be able to cancel the order. | 1. After login into admin account, there will a option called cancel item for the admin to cancel the order. 2. If the user click cancel, product remove from My Cart table. | Low | Sprint 2 | 13
US_9 | Order Delivery | Admin | Ability of the system to,as a admin should be able to show status of the order as delivery. | 1. After login into admin account, there will a option called delivery item for the admin to deliver the order. 2. If the user click delivered, then the product status will show as delivered in My Cart table. | High | Sprint 2 | 5
US_10 | Forgot Password | User | Ability of the system to, if a user forgot password, user can reset the password | 1. A FORGOT PASSWORD option will be displayed at the login page . 2.After clicking onto that option, it will be redirected. 3. The user should give the details like email,mobile number,security question and give new password and save it. 4.Once the user is done with the above procedure the new password gets updated and shows the message like password successfully changed. | Low | Sprint 2 | 13
US_11 | Message us | User | Ability of the system to, the user should be able to give their feedbacks | 1. To avoid problems the users can give feedback . 2. Through this we would be able to know the problems like unreliable delivery and customer's opinion over products. | Low | Sprint 2 | 13
US_12 | About | User | Ability of the system to, the user should be able to view about and came to know about this application. | 1. The user can view about the application by clicking the option called About in home page and then it redirected . 2. Through this the user can able to know about this application and able to know about admin mail id and contact number. | Low | Sprint 2 | 13
US_13 | Contact Us | User | Ability of the system to,user can contact the admin if he is having doubts | 1. The user can view about the application by clicking the option called contact in home page and then it redirected . 2. Through this the user can able to know about this application and able to know about admin mail id and contact number. | Sprint 2 | Sprint 2 | 13
US_14 | Payment process | User | Ability of the system to, the user should be able to pay the amount for the Product | 1. The user can pay the cash on delivery time or on online payment. 2. The user should give the correct details such as address,city,state way of payment,transaction id and mobilenumber. 3.After posting the successful payment, they can able to generate the bill for their confrimation. | High | Sprint 2 | 5
US_15 | Logout | User | Ability of the system to,the user should be able to logout | 1. According to their convenience, the user can sign out the application. | Critical | Sprint 2 | 3

## Charts
Release Burndown
Only edit shaded columns, others are calculated
Sprint | Story points |  |  | Percent Complete | Min | Max
| Remaining | Done | Variation
1 | 100 | 75 | 0 | 43% | 0 | 100
2 | 170 | 150 | 145 | 47% | -145 | 25
3 | 190 | 120 | 135 | 39% | -135 | 55
Yes
No

## Sheet1 (hidden)
0
5
10
20
30
50
80
130
200
400
1000